## Blank Assessment
Self-Assessment and Planning Tool for implementing PTIE recommendations and general equity-minded improvements to reward and advancement processes.
| Refers to approved PTIE recommendations and related discussion in Science paper https://ptie.org/ptie-recommendations/ | Describe how the unit currently addresses processes related to the recommendation. Identify current positive action aligned with the recommendation and areas for growth and improvement. | Describe how implementing the recommendation could create opportunity and improve conditions in the unit. | Describe key anticipated barriers to implementing change related to the recommendation. distinguish between perception and reality. | Identify specific (short- or medium-term) actions that work towards implementing the recommendations and harnessing the opportunity. | Estimate when work on the action will begin and how long it will take. | Identify a person, unit, or group who will lead this work and be accountable to deliver on the action. | Cross reference how actions toward this recommendation align with the unit Diversity Plan. | Identify how the you will assess progress toward the recommendation and/or actions identified in column F. | Identify long-term and larger-scale ambitions and/or future work that would build on current actions.
PTE Recommendation Reference | Recommended Item | Current process | Opportunity | Key Barriers | Actions | Timeline | Who will Lead | DEI strategy connections | Assessment | Future work
Mechanical/ Personal Statement | Personal Statement Guidance
Mechanical/ External Review | External Reviewer Guidance
Mechanical/ External Review | External Reviewer Network
Process/ Validation | Resources to Validate Societal Impacts
Process/ Evaluations | Annual Evaluations
Process/ PDs | Position description updates
Process/ Bias | Bias Training
Process/ Process Consulting | Process consultant
Process/ DEI | Engage with DEI office
Process/ DEI | DEI Commitment to Action
Process/ External Review | External Reviewers COI/AOI considerations
Process/ I&E Training | I&E Training Plan
Process/ I&E Leadership Engagement | I&E Leadership Engagement

## Examples
Examples for Piloting - Living Document DRAFT (fictitious amalgam unit, based on aggregate data and knowledge of the PTIE team)
PTE Recommendation Reference | Recommended Item | Current process | Opportunity | Key Barriers | Actions | Timeline | Who will lead | Assessment Strategy | DEI strategy connections | Future work
Mechanical/ Personal Statement | Personal Statement Guidance | Recommended items to include, no set format, statements not required. | Help faculty focus statement on impacts not easily identified by those outside of their own scholarly area | Mentor/chair time to support faculty in this process | Host annual lunch sessions to hone personal statements. Require personal statements at 3 year reviews and with P&T package. | Immediate - statement preparations for spring 2023 reviews. | Small committee of recently tenured faculty in collaboration with 2 trusted external reviewers | Qualitative measures: Faculty better articulate their unique impacts; reviewer clarity; academic outputs contextualized in impact how they support university mission. | Expressing alignment between individual scholarly effort and institutional values. Articulating tradeoffs in terms of impacts. e.g. less NSF research in favor of more collaboration with industry. Or less teaching core courses in favor of developing I&E curriculum and experiential learning.
Mechanical/ External Review | External Reviewer Guidance | We are very clear with external reviewers, we provide Position Descriptions (PDs) and describe how a PD might be different than what reviewers expect. | We want reviewers to review performance in relation to actual PD, not their conception of what the position should be. | Old patterns, gatekeeping, quick/sloppy reviews | Develop a flexible rubric that can be customized for the individual, their scholarly strengths and their PD. | Next Academic Year reviews (e.g. fall letter requests) | See above | Completed rubrics, P&T committees perceptions of rubric value | Is likely to remove bias associated with omission of reviews on certain aspects of scholarship or false weighting of different scholarly activities.
Mechanical/ External Review | External Reviewer Network | Ad hoc, whoever we can get without a COI - an external reviewer resource could be developed through the national PTIE Coalition members | Reviewers that understand the goals and values of our university and college. Economy of scale, using a network already steeped in I&E | Social capital with repeat reviewers, asking too much of colleagues | Explore existing networks to tap into - for I&E I-Corps Fellows, PTIE coalition, Innovation Advocates at OSU. Provide more explicit guidance to Department Chairs/Heads for collecting letters. | Over the next two years | A small committee of mixed tenured and pre-tenure faculty will assemble in a working group. | Survey of Department Heads on value of improved instructions on letter quality. Solicit insights from pre-tenured faculty. | Improve quality of external letters - particularly for URM that may not have as extensive a professional network.
Process/ Validation | Resources to Validate Societal Impacts | Judgement call of external reviewers and committee | More information to assist with assessing candidates who perform unusual scholarship in the disciplines. Allow candidates to better defined their own metrics. | Time, bias of some reviewers to applied research/impact. | Bring together pre-tenure faculty to explore altmetrics and DORA resources salient to their academic practice. Discuss the use of altmetrics with senior faculty and P&T committees. | Fall 2023/Winter 2023 | Pre-tenure faculty (years 1-4) with the help of social scientists and an external advocate. | Completion of a discipline specific altmentrics set of resources and some updates to the college/department handbooks on the use of altmetrics. | Recent research suggests that underrepresented minority (URM) college students, and especially first-generation URMs, may lose motivation to persist if they see science careers as unable to fulfill culturally relevant career goals. See https://doi.org/10.1187/cbe.16-01-0067
Process/ Evaluations | Annual Evaluations | Reviews are required annually, however many faculty do not receive in depth reviews. | More regular and in depth (annual) reviews that have embedded in them as assessment of workload in relation to impacts (i.e. is someone spending a lot of time on a high impact activity that is not well accounted for in P&T process - e.g. industry partnerships for student experiential learning). | Assessing and valuing different types of work, difficult to compare faculty to each other. | Gain better understanding of existing processes on campus, speak with Dept Chairs/Heads and Deans about opportunities to better link annual eval to position descriptions and P&T process. | Next Academic Year with all faculty years 1-4) and years 5 and 6 if they choose. | Department Chair, with support from assigned mentors | Survey of faculty evaluates process annually. Survey chairs/heads on impact of changes. Improvement over time | Improved communication between supervisor and faculty member on performance can reduce confusion and bring issues to the surface sooner.
Process/ PDs | Position description updates | Not currently done, most PDs in the department are a standard breakdown (e.g. 45/45/10 or 40/40/20) | Performance could be better connected to specific strengths and impacts generate by faculty member. Eliminate the piling on effect and make tradeoffs more explicit and assessable. | Fairness within the department, HR processes to change PDs, perception concerns (e.g. "lowering the bar")for making PDs more tailored to individual strengths / department needs; bugetary concerns related to the income/cost recovery associated with teaching and research in the department. | Poll/survey the faculty on the degree to which their PD matches actual work and reflects the ways in which they are making impacts. Consider providing guidance to Dept Chairs/Heads that PDs need not be uniform - but rather aligned with strengths of individual and needs of unit. Dean level assessment of the collection of work needed to maintain fiscal health of the college (e.g. the faculty must collectively maintain 40% reserach and 40% teaching - so the break down must average out) - see the faculty as a community play to their individual strengths. | During annual reviews beginning 2023. Fiscal Assessment in Summer 2022 (with Sherm Bloomer) | Direct supervisors with support of HR coordinators. Deans and Fiscal administrators | Survey of Department Heads/chair and faculty on impact from changes. | Addresses silent reality that URM and women currently tend to get a disproportionate service load. Makes process more equitable for all involved
Process/ Bias | Bias Training | Just the university compulsory trainings on bias, no specific P&T related training. | Reduce risk/liability of bias accusations, more importantly reduce incidence of bias in review, improve retention of minoritized faculty | Time and skilled trainers, resistance from P&T committees | Collaborate with Search Advocacy to develop a P&T committee engaged Bias training. | Next Academic Year and Annually thereafter | VPR/Faculty Affairs - could coordinate this at the institutional level in collaboration with DEI Office. | Pre/post survey of participants. Perceptions of underrepresented faculty and experts in DEI Office on the value of this effort. | Culture change, retention, clarity of process, reduction of bias and micro-aggressions in review processes. | Training with external reviewers, extension of the nationwide SA network.
Process/ Process Consulting | Process consultant | None, however several P&T committee members are trained Search Advocates and have attended other trainings. | Additional protection and validity. Avoid issues and bias incidents before they harm faculty or the departments. Include a neutral broker in the process who does not have relationships with the candidate | Lack of skilled consultants, service time is limited and faculty are already over committed on this type of intuitional service. | Work with P&T Committee and Chairs to identify feasible points in the process for a consultant to advise and point out areas where there is a risk of bias. Work with SA to develop a P&T review module for SA training to become process consultants. | This summer for initial explorations. Training Next Academic Year and Annually thereafter | DEI lead for the college; VPR/FA - could coordinate this at the institutional level in collaboration with OID. | Availability of consultants, self-assessment of both the consultant and the P&T committee and the Dept Chair. | Culture change/practice change/disruption of biased norms, reduction of the influence of systemic bias. | Expand to the nationwide network od institutions with serach advocacy.
Process/ DEI | Engage with DEI office | Not part of our process | Understand how individual faculty are contributing the institutional DEI goals; understanding the actual issues faculty minoritized faculty and seek strategies to reduce harm and bias that contributes to attrition. Provide opportunities for faculty to engage in a supportive network and receive reward for their DEI service. | DEI office doesn't understand how we assess people and what is considered impact. | Meet with DEI Office to learn about opportunities that exist or could be developed to support pre-tenure faculty. | Fall 2022/Winter 2023 | DEI lead for college in collaboration with the PTIE team and FA. | Evidence of improved understanding and identification of mutually beneficial program and actions between unit and institutional DEI office. | Interface with the DEI office and alignment with the institutional diversity plan is part of our unit effort.
Process/ DEI | DEI Commitment to Action | All faculty must articulate how they contribute to DEI in their personal statements | Make the purpose and goals of this requirement more meaningful and discover valid way to assess success. | Hard to do; hard to assess. Perception that this costs money with no source of funding. | Use College DEI strategy to make DEI contributions more explicit in PDs. Support faculty in the development of metrics/altimetric to assess DEI contributions; update handbook | Next Academic Year | Faculty with the support of College DEI lead, DEI Office, mentors, and senior faculty. | Updated PDs, availability and use of applicable measures. | This action is directly identified in our DEI plan.
Process/ External Review | External Reviewers COI/AOI considerations | Reviewers cannot have any knowledge of the candidate. We are very strict that this consitutes a conflict of interest. | Explore hidden bias of zero connection, compare with potential for bias with some connection. Reviewers with alignment of interests may provide more comprehensive and meaningful review of impacts. | Validity of process. Fairness. Perception that alignment = nepotism | Look for reviewers with shared social identities; Adjust COI to be a more nuanced process framed as Alignment of Interests - allowing reviewers and P&T committees to assess on specific criteria; invite faculty to suggest reviewers; update handbook. | Next Academic Year | P&T committee with the help of an equity advocate from outside the college. | Incidence of COI/AOI violations or concerns.
Process/ I&E Training | I&E Training Plan | Each faculty member carves their own path - I&E path can be difficult for pre-tenure faculty. | Support faculty in being successful with I&E and avoid false starts and wasted energy. Establish this supported I&E path with some milestones and specific annual assessment of progress | Without I&E activity counting, current offerings are easily ignored. Robust informational and training resources are currently available. | Work with PTIE and the Research Office to better understand opportunities and connect I&E interested faculty into those opportunities | Start this summer with ongoing engagement | Deans, Assoc. Deans for Research, Chairs, with Advantage Staff in the Research Office. | Level of increased faculty and student engagement with I&E programs | Ensure messaging is reaching women and underrepresented faculty and Students | Create a model engagement program where messaging is targeted and facilitated by colleges and departments.
Process/ I&E Leadership Engagement | I&E Leadership Engagement | The Innovation Impact Program provides outreach to faculty students and staff for program engagement. | Non I&E faculty better understand what I&E, how it is done and what impact looks like. | With I&E activity not counting, faculty engagement can be challenging. There is an effort underway through the Innovation Advocates which could help. | Robust informational and training resources are currently available. A new college engagement plan in currently being developed between the Research Office, Col. of Engineering, and Industry Partnerships | Next Academic Year | Dean's, Assoc. Deans for Researchs, Chairs and Advantage Staff in the Research Office | Level of increased faculty and student engagement with I&E programs | Colleges aid in engagement with women and underrepresented faculty and students | Create a fellows program; host and industry partnership event, informational programming from Federal agency officers, and other engagement programs